## Part B - Targets and Initiative
2014/15 Quality Improvement Plan for Ontario Hospitals
"Improvement Targets and Initiatives"
Weeneebayko Area Health Authority 19 Hospital Drive Box 664
AIM |  | Measure | [7 empty] | Change
Quality dimension | Objective | Measure/Indicator | Unit / Population | Source / Period | Organization Id | Current performance | Target | Target justification | Priority level | Planned improvement initiatives (Change Ideas) | Methods | Process measures | Goal for change ideas | Comments
Patient-centred | Improve patient satisfaction | In-house survey: provide the percent response to a summary question such as the "Number of patients responding yes to the question "In your opinion, does WAHA provide good quality care?" | % / All patients | In-house survey / 2013-2014 | 973* | 59 | 64 | To improve our patient satisfaction rate by 5% | Improve | 1)WAHA will continue to implement a patient satisfaction survey implementation in the emergency departments for 2014-2015 at Weeneebayko General Hospital (WGH), Fort Albany Hospital (FAH) and Attawapiskat Hospital (AH) | WAHA's Quality Department will check-in with each site quarterly to see how many surveys have been filled out. WAHA will encourage staff to ask patients in each ER department to fill out surveys as deemed appropriate. | The number of patients surveyed per quarter will be tracked per listed site and the % of patients answering yes to the question "in your opinion, does WAHA provide good quality care" will be recorded quarterly | To ensure the patients from WAHA emergency departments are filling out surveys. WAHA would like to obtain at least 50 surveys per quarter from all the sites combined. | Stretch target: 100% reported satisfaction in the quality of care received by patients as identified in the annual patient satisfaction survey
[10 empty] | 2)Communication intervention | WAHA will encourage staff to ask patients in each ER department to fill out surveys as deemed appropriate | Number of times WAHA communicates with its staff at each site per quarter | To have more patients fill out more surveys for 2014-2015 | Direct patient engagement strategies are believed to enhance participation rates and have been successful for other initiatives within WAHA
[10 empty] | 3)Incentive intervention | WAHA will offer the opportunity for patients to win quarterly prizes for filling out a survey. Signage will be posted in each site's ER department to inform patients of the quarterly contest. | The number of signs advertising the contest in each site's ER department will be tracked, along with the number of patients surveyed per quarter | Increased participation from patients in filling out surveys | Incentive initiatives have been successful in increasing patient participation rates for WAHA in other community based projects
[10 empty] | 4)Feedback intervention | Quarterly results from patient satisfaction survey provided to Senior Management/Middle Management/Staff | Number of communication activities conducted to engage Senior Management/Middle Management/Staff at WAHA | To provide continuous feedback to all WAHA employees on patient sentiment as it relates to the quality of service they received | Progress evaluated quarterly by all WAHA staff
| Improve staff satisfaction | In-house survey: provide the numerical response to a summary question such as the "On a scale of 1 to 10 (1 being the lowest rating, 10 being the highest rating) how would you rank WAHA as an employer?" | % / N/a | Staff survey / 2014-2015 | 973* | 5.1 | 5.1 | To evaluate the findings from the 2013-2014 staff satisfaction survey and identify two major projects as areas requiring improvement. These projects will be developed and implemented in 2014-2015. | Maintain | 1)Measurement intervention | Identification of 2 major areas requiring improvement from survey data collected | 2 major areas requiring improvement identified | 2 major areas requiring improvement addressed by fiscal year end 2014-2015
Safety | Increase proportion of patients receiving medication reconciliation upon admission | Medication reconciliation at admission: The total number of patients with medications reconciled as a proportion of the total number of patients admitted to the hospital. | % / All patients | Hospital collected data / Most recent quarter available (e.g. Q2 2013/14, Q3 2013/14 etc) | 973* | CB | 11 | 11 medication reconciliations were completed on CCC patients in Fort Albany Hospital FY 2013-2014 and WAHA will establish a baseline for medication reconciliations completed at WGH FY 2014-2015 | Improve | 1)Gap analysis | Create a standardized data collection process at WGH |  | To gather data in order to establish a baseline for 2014-2015 | Stretch target: eliminate undocumented intentional discrepancies and unintentional discrepancies by reconciling medication for those patients who are admitted to WGH's inpatient department
[10 empty] | 2)Policy standardization | Review policies and procedures from WGH | Number of policies and procedures pertaining to medication reconciliation reviewed at WGH quarterly FY 2014-2015. | Standardization of policies and procedures at WGH pertaining to medication reconciliation | Stretch target: eliminate undocumented intentional discrepancies and unintentional discrepancies by reconciling medication for those patients who are admitted to WGH's inpatient department
[10 empty] | 3)Process intervention | Use a standardized reconciliation form to implement upon admission, outlining the number of admission medications reconciliations completed | 70% of patients upon admission going through the medication reconciliation process | 100% compliance as described in the process measures section by March 31, 2015 | stretch target: 100% of patients in admissions going through the medication reconciliation process
[10 empty] | 4)Communication interventions | Create a medication transfer letter that could to be sent to receiving institutions if external transfer is required. Quarterly communiques will also be disseminated to staff by the Quality Department. | Number of medication transfer letters sent to receiving institutions, compared to the number of patients sent to receiving institutions. The number of quarterly communiques disseminated to staff will also be tracked. | To decrease number of adverse events due to medication errors and to inform staff on the progress of the medication reconciliation project. | Stretch target: 0 adverse events due to medication errors
| Reduce hospital acquired infection rates | CDI rate per 1,000 patient days: Number of patients newly diagnosed with hospital-acquired CDI, divided by the number of patient days in that month, multiplied by 1,000 - Average for Jan-Dec. 2013, consistent with publicly reportable patient safety data. | Rate per 1,000 patient days / All patients | Publicly Reported, MOH / 2013 | 973* | 1 | 1 | 1 case of CDI reported FY 2013-2014 | Maintain | 1)
|  | Hand hygiene compliance before patient contact: The number of times that hand hygiene was performed before initial patient contact divided by the number of observed hand hygiene indications for before initial patient contact multiplied by 100 - consistent with publicly reportable patient safety data. | % / Health providers in the entire facility | Publicly Reported, MOH / 2013 | 973* | 82.8 | 85.5 | WGH will work to maintain or exceed its current performance. WGH is currently at 90% compliance before patient-environment contact and is already above the provincial average. Fort Albany Hospital (FAH) hand hygiene compliance before patient-environment contact was 68% and FAH will work to improve its compliance by at least 6% FY 2014-2015. Attawapiskat Hospital (AH) increased its compliance rates significantly from 2012-2013 and reported before patient-environment contact compliance of 69% FY 2013-2014, AH will work to improve its compliance rate by at least 5% FY 2014-2015. | Improve | 1)WAHA will identify individuals to serve as staff auditors at WGH, FAH and AH | WAHA will work in collaboration with its Amublance Service Provider (James Bay Ambulance Services) to train auditors to assist with compliance checks | The number of hand hygiene audits completed per site will be tracked on a quarterly basis | Train auditors via a role-modelling and mentoring approach in collaboration with the Infection Control Nurse. Targets for the number of audits to be completed at WGH, FAH and AH to be set for each auditor | Stretch target: 100% compliance in all sites
[10 empty] | 2)Training intervention | "Just Clean Your Hands" training will be provided to front line staff | Number of hand hygiene training sessions delivered to front line staff per quarter Number of staff participating in training session per quarter | Increasing staff's hand hygiene compliance rates before patient contact | All front line staff are trained in each of WAHA sites on the "Just Clean Your Hands Curriculum"
[10 empty] | 3)Communication interventions | Quarterly staff communiques will be disseminated by the quality department to staff, informing them of quarterly hand hygiene compliance rates. Signage will be developed and posted to remind staff to wash their hands in patient care areas before patient interactions. | Number of staff communiques disseminated per quarter and the number of signs developed and posted within patient care areas | Staff continuously informed on the importance of hand hygiene, leading to better compliance | WAHA to identify communication mediums which are most effective in engaging staff at WGH, FAH and AH
[10 empty] | 4)Feedback intervention | Senior/Middle Management meetings will be held to discuss performance objectives | Number of meetings held with Senior/Middle Management groups | Leadership engagement to elicit feedback from each leadership group to improve hand hygiene compliance | Meeting schedule incorporated into performance management cycle
| Avoid Patient falls | Percent of complex continuing care (CCC) residents who fell in the last 30 days. | % / Complex continuing care residents | CCRS, CIHI (eReports) / Q2 2013/14 | 973* | CB | 0.37 | 0.37% rate achieved at Fort Albany Hospital (FAH) Q1-Q2 2013-2014. This project will be carried over to Attawpiskat Hospital (AH) and baseline data will be collected at AH. A system to collect data in order to meet provincial standards will be developed. | Maintain | 1)Gap analysis | Needs assessment with staff to determine training needs | Number of staff who require training supports | Training needs identified for staff - gap areas identified and assessed | Training standardized and delivered to staff
[10 empty] | 2)Training intervention | Deliver falls prevention curriculum to staff (RNAO Best Practice Guidelines and Canadian Falls Prevention Curriculum) Deliver training on the 3 D's (delirium, depression and dementia) to staff | Number of staff who receive training on best practice guidelines and for the 3 D's. | Promoting safe mobility; risk assessments; multi-disciplinary strategies; alternatives to restraints and/or other restricted devices | Stretch target: 100% of high risk patients are identified
[10 empty] | 3)Measurement Intervention | Implement the data collection process to identify baseline for falls as created in FAH and utilize it at AH | Number of patient falls identified per month | Baseline data will be collected and recorded for fiscal year 2014-2015 at AH | stretch targets: - zero cases reported of patients who fell - zero cases who sustained significant harm - zero who sustained injury - zero who died as a result of a fall
[10 empty] | 4)Communication intervention | Quarterly communiques dissemintated to staff via the quality department | Number of staff communiques disseminated per quarter | Feedback loop | Engagement of staff
[10 empty] | 5)Process intervention | Use Fall Scale Assessment Record to assess risk with all patients | Completing a fall risk assessment on at least 70% of all patients within 8 hours of being admitted to WAHA | 100% staff compliance for completion of fall risk assessments as described in the process measures by December 2014 | stretch target: completing a fall risk assessment on 100% of all patients within 8 hours of being admitted to WAHA
| Reduce rates of deaths and complications associated with surgical care | Surgical Safety Checklist: number of times all three phases of the surgical safety checklist was performed (briefing, time out and debriefing) divided by the total number of surgeries performed, multiplied by 100 - consistent with publicly reportable patient safety data. | % / All surgical procedures | Publicly Reported, MOH / 2013 | 973* | 98.6 | 100 | To set future performance objectives to ensure 100% compliance | Improve | 1)Training intervention | Review current literature on best practices. Incorporate SSCL orientation into the surgical orientation manual. Develop signage to remind operating room staff to complete the SSCL. | SSCL orientation incoporated in surgical orientation manual and signage posted within operating room | Best practices are implemented consistently and signage is posted within operating room to remind staff to complete the SSCL for each surgical procedure
[10 empty] | 2)Increase rigour of audits | Audit the three phases of the SSCL (briefing, time out and debriefing) and document completion of each phase during operative procedures | Number of audits completed where three phases of SSCL were completed divided by the total number of surgeries completed. These figures will be compiled on a quarterly and yearly basis. | To improve compliance in completing the SSCL for each surgical procedure | The IFC Nurse and OR have been communicating every month to assess and monitor performance
[10 empty] | 3)Measurement intervention | Calculate compliance rate by taking average monthly rates from January 2014 to December 2014 | Number of times the SSCL was performed over the total number of appropriate surgeries | Data will be collected and recorded. Surgical checklist compliance will also be monitored monthly and timely feedback will be provided by the IFC Nurse to the Operating Room staff | Stretch target: 100% compliance in completion of surgical safety checklists
[10 empty] | 4)Communication intervention | Surgical safety checklist compliance figures posted quarterly and yearly on weeneebaykohealth.ca. A staff communique will also be developed to report compliance figures quarterly to staff. Public education will also be offered by posting information and frequently asked questions about the surgical safety checklist on weeneebaykohealth.ca and also within the OR department. | Number of times quarterly/yearly surgical safety checklist compliance figures were posted on weeneebaykohealth.ca. Number of quarterly communiques disseminated to staff. Public education information posted on weeneebaykohealth.ca and within the OR department. | 100% compliance by March 31, 2015 | Progress evaluated quarterly/yearly and presented to public
[10 empty] | 5)Process intervention | Use of 3 phase checklist for every surgical procedure in the operating room and investigation of cases where SSCL did not occur to understand barriers. | Number of times the 3 phase checklist was completed on 100% of all patients awaiting surgical procedures in operating room. Findings reviewed each month by IFC Nurse in conjunction with OR staff. | 100% compliance by March 31, 2015
Note on D1: hover help: General instructions for completing this excel spreadsheet: 1. Insert your hospital's name and logo where indicated. 2. Please do not edit or modify the text provided in Columns A, B and C. 3. When inserting new rows (i.e. hospital specific information, new indicators, etc.), please ensure an entire row is inserted as opposed to a single cell so that the hovers remain intact and correspond to the cell the information is intended for. 4. “Hover help” has been provided where appropriate to assist with completion of this spreadsheet. These are comments that display when your mouse ‘hovers’ over the cell. The comments provide brief reminders about how to complete this excel spreadsheet. It is recommended that you review the Guidance Document including the Appendices for more information. Refer to Appendix F in the Guidance Document for an example of a completed row for a sample indicator.